## Detailed Project Timeline
Task Name | Duration | Responsible
Health Insurance Open Enrollment Campaign | 195d
Project Briefing Kick Off | 5d | Client
Obtain all Stakeholders Information | 3d | Client
Approve Campaign Brief | 1d | Client
Media and Creative Strategy Kickoff | 1d | Agency
Media and Measurement Strategy | 50d
Present Media and Measurement Strategy, Flowchart & Projections | 30d | Agency
Provide feedback | 2d | Client
Updates to Strategy Presentation (R2) | 2d | Agency
Approve Media & Measurement Strategy | 1d | Client
Media Setup | 15d | Agency
Data Analytics and Audience List | 30d
Measurement Plan | 10d | Agency
Provide audience list sizing and models profiles | 10d | Client
Set up measurement KPIs, tracking and reporting dashboard | 9d | Agency
Deliver 1P data to media partners | 1d | Client
Creative Concepting | 30d
Develop creative concepts | 20d | Agency
Present concepts | 1d | Agency
Revisions | 2d | Agency
Present concepts R2 legal | 1d | Agency
Legal review and provide comments | 5d | Client
Share final concepts for approval | 1d | Agency
Creative Production, e.g. Video | 50d
Kickoff | 1d | Agency
Storyboarding | 7d | Agency
Share storyboards | 1d | Agency
Provide feedback | 3d | Client
Storyboard revisions | 5d | Agency
Share revised storyboards | 1d | Agency
Legal review, comments, approval | 10d | Client
Rough cut editing | 5d | Agency
Present rough cut | 1d | Agency
Provide feedback | 3d | Client
Rough cut revisions | 5d | Agency
Approve | 2d | Client
Color correction | 1d | Agency
Final Rendering | 2d | Agency
Files Release | 3d | Agency
Website/UX Development | 30d
Kickoff | 1d | Agency
Creative/UX development - landing page wireframes | 10d | Agency
Revisions | 5d | Agency
Review with IT/Technology team for implementation | 5d | Client
Revisions | 2d | Agency
Final approval of creative | 1d | Client
Release files to IT for implementation | 5d | Agency
Final QA (including tags) in production environment and launch | 1d | Client